**Progress report 1**

*(a) what specifically you have accomplished since the last progress report,*

* Clean and tidy the following Data:
  + GALI – 2013 to 2019 (done)
  + GEM NES – 2016 (done)
  + GEM APS – 2016 (done)
  + GCI 2018 (in progress)
* Join GALI and GEM data (done)
* Join data to GCI (in progress)
* Constructed the following variables for venture data:
  + Human capital index (done)
  + Social capital index (in progress)
  + Financial capital index (in progress)
  + Gender decomposition (done)
  + Attention level variables to human capital, social capital, and financial capital (done)
  + Capital structure variables (for a potential DV)

*(b) any necessary revisions to your product moving forward,*

No revisions. I must complete all the tasks above by end of week 4

*(c) anticipated timelines for the remaining components of your product.*

Week 5:

* Codebook for country variables: Done
* Focus on constructing all the country based variables.
* Start trying out the papaya package

Week 6-7:

* Final variable construction
* Analysis and plots

Week 8-9:

* Writing findings
* Incorporating to publish using papaya